## Jira Backlog
Issue ID | Title | Description | Issue Type | Priority | Story Points | Assignee | Branch Name | Status | Sprint
CC-1 | Setup Project Structure | Initialize Flask project and folder structure | Task | High | 3 | Deepesh Sharma | feature/setup-project | To Do | Sprint 1
CC-2 | Design Chat UI | Create responsive chat interface using HTML/CSS/JS | Story | High | 5 | Aman Verma | feature/chat-ui | To Do | Sprint 1
CC-3 | Implement FAQ Module | Create JSON-based FAQ response handling system | Story | Medium | 5 | Priya Singh | feature/faq-module | To Do | Sprint 1
CC-4 | Integrate GPT-2 Model | Integrate HuggingFace GPT-2 for fallback response | Story | High | 8 | Deepesh Sharma | feature/gpt2-integration | To Do | Sprint 2
CC-5 | Create Chat API Endpoint | Develop Flask /chat POST endpoint | Task | High | 3 | Rahul Mehta | feature/chat-api | To Do | Sprint 2
CC-6 | Database Integration | Store chat logs in SQLite database | Story | Medium | 5 | Priya Singh | feature/database-logs | To Do | Sprint 2
CC-7 | Add Input Validation | Sanitize user inputs to prevent injection | Task | Medium | 3 | Aman Verma | feature/input-validation | To Do | Sprint 2
CC-8 | Implement Error Handling | Add exception handling for API and model errors | Task | Medium | 3 | Rahul Mehta | feature/error-handling | To Do | Sprint 3
CC-9 | Render Deployment Setup | Prepare configuration for Render deployment | Story | High | 5 | Deepesh Sharma | feature/render-deployment | To Do | Sprint 3
CC-10 | Create README & Documentation | Write project documentation and usage guide | Task | Low | 2 | Priya Singh | feature/documentation | To Do | Sprint 3
CC-11 | Testing & Bug Fixing | Perform unit testing and resolve issues | Story | High | 8 | Aman Verma | feature/testing-bugfix | To Do | Sprint 4
CC-12 | UI Improvements | Enhance UI animations and responsiveness | Story | Medium | 5 | Rahul Mehta | feature/ui-enhancements | To Do | Sprint 4