## College Chatbot Jira Backlog
Issue ID | Title | Description | Issue Type | Priority | Story Points | Assignee | Branch Name | Status | Sprint
CC-1 | Project Setup | Initialize Flask project and repository structure | Task | High | 3 | DEEPESH SHARMA | feature/project-setup | To Do | Sprint 1
CC-2 | Design Chat UI | Develop responsive chat interface using HTML/CSS/JS | Story | High | 5 | MOHD KABIR KHAN | feature/chat-ui | To Do | Sprint 1
CC-3 | FAQ Knowledge Base | Create JSON-based FAQ data for chatbot | Story | Medium | 5 | VINIT KUMAR | feature/faq-module | To Do | Sprint 1
CC-4 | Flask Chat API | Develop /chat API endpoint in Flask | Story | High | 5 | KUNAL DIWAKAR | feature/chat-api | To Do | Sprint 2
CC-5 | GPT-2 Integration | Integrate GPT-2 model using transformers | Story | High | 8 | DEVANSH | feature/gpt2-integration | To Do | Sprint 2
CC-6 | Database Integration | Store chat logs in SQLite database | Story | Medium | 5 | SHIVAM RATHORE | feature/database-logs | To Do | Sprint 2
CC-7 | Input Validation | Sanitize user input to prevent injection | Task | Medium | 3 | DIVYANSH PATEL | feature/input-validation | To Do | Sprint 3
CC-8 | Error Handling | Implement exception handling for APIs | Task | Medium | 3 | ANUSHA SRIVASTAVA | feature/error-handling | To Do | Sprint 3
CC-9 | Deployment Setup | Prepare project for deployment on Render | Story | High | 5 | AACHAL SONI | feature/render-deployment | To Do | Sprint 4
CC-10 | Testing & Debugging | Perform unit testing and bug fixing | Story | High | 8 | SAURABH CHAUHAN | feature/testing-bugfix | To Do | Sprint 4